## Goals
CDP | Concerns | Goals | Specific, Measurable Pinpoints
1.0 Purpose & Identity | Helping families that resist is hard | 1.1. Families report that they felt supported & validated | 1.1.1 Supervisors will use BST to teach associates active listening skills once per quarter, beginning March, 2020
1.1.2 Associates will restate what others have said to them (e.g., "So, what I hear you saying is…") during conversations with each other, kids, parents, and teachers, as observed by colleagues after initial training.
1.1.3. Associates will express empathy (e.g., "That sounds hard. Anyone would feel that way.") during conversations with each other, kids, parents, and teachers, as observed by colleagues after initial training.
| Helping staff that don't trust BA science is hard | 1.2. Staff report that the way supervisors talk to them is relatable | 1.2.1. Admins will use BST to teach supervisors and staff relatable ways to discuss company initiatives once per quarter beginning, March, 2020
1.2.2. Associates will use non-aversive ways to express ACT concepts (e.g.,. Yeah, I'm working on taking my thoughts lightly, too")
2.0 Equivalent Resources/Reinforcers | The distribution of high-value material resources is not transparent | 2.1. Every center gets fair distribution of ACME resources | 2.1.1. Admins will provide quarterly reports about available resources, where the company is at, to see if the resources are available, beginning March, 2020
2.1.2. Admins will analyze resources and redistribute yearly, beginning _____
| Trainers sometimes have to help with crises and are left with insufficient time to do their jobs | 2.2. We have written clearly defined job roles | 2.2.1. Admins will clearly define all of the roles for each position for the company, beginning _____
2.2.2. Admins will ask associates for input in writing job descriptions, beginning March, 2020
2.2.3. Associates will group responsibilities for each role
| Unequal access to supervisors | 2.3. We hold regular supervisory meetings and reschedule cancelled meetings as needed or requested by staff | 2.3.1. Supervisors will provide regular bi-weekly meetings or reschedule if unable to meet as scheduled, beginning March, 2020
2.3.2. Supervisors will distribute supervision time among staff/clients equitably and provide rationales as needed when there are notable imbalances
3.0 Decision-Making | Unclear process for making decisions and relaying information about decisions to others. Unclear accountability; weak follow through on initiatives. | 3.1. We have codified systems for decision-making, on-boarding staff, piloting, and implementing new strategies | 3.1.1. ACME will make organizational decisions in teams that include representatives from each site and position (tech, lead, trainer, BCBA, admin).
3.1.2. Decision teams will provide rationales for decisions and provide associates time to comment prior to implementation. When possible, rationales will refer back to organizational values.
| Initiatives do not always lead to desired outcomes. We need transparent evaluation and revision procedures | 3.2. Decision teams collect data, evaluate, revise, and report back the community on the effectiveness of inititives | 3.2.1. Associates will keep track of decisions and utilize rotating committee for reviewing these decisions.
3.2.2. Associates will make data based decisions and have frequent revisions during this process.
| Our decision teams lack representation from diverse groups (e.g., people of color, neurodiverse individuals, LGTBQ+) | 3.3. Our decision teams include people from all walks of life. When this is impracticable, we strive toward cultural competence and awareness of our biases, privilege, and power. | 3.3.1. Associates will review decisions for their cultural competance, discussing them in light of culture, privledge, and bias.
3.3.2. Associates will develop a system for how to handle clients behaviors that are offensive, and also be aware of our own bias.
3.3.3. ACME will write diversity goals for recruiting members of decision teams.
4.0 Monitoring Agreed Bxs | We have too many tasks; we feel confused about what we're supposed to doing. | 4.1. We provide clear performance expectations to employees at all levels of the organization. | 4.1.1. By April 1, 2020, trainers (with support from supervisors, lead techs, and admins) will design modules that specify the parties responsible for monitoring and the scheduled frequency of monitoring. For example, monitors will shadow at least a half hour per shift during a tech's first month, a half hour per week on the average after that until a new hire has completed their probationary period, and a half hour per month after that.
4.1.2. Trainers, supervisors, lead techs, and admins will clearly specify the boundaries of the monitoring tasks.
4.1.3. Trainers will create job aids that correspond to the job description for every role.
4.1.4. Trainers and others involved in designing systems for monitoring agreed upon behaviors will establish an ongoing collaboration with admin.
| We do not know who is tasked with ongoing monitoring of others' behaviors. At the moment, techs are unofficially supervised by trainers, and this leads to hard feelings and ongoing conflicts. | 4.2. Our monitoring schedules assure that everyone is supported enough to master their jobs. | 4.2.1. Trainers, supervisors, lead techs, and admins will provide a written, detailed, and consistent monitoring schedule. The schedule will specify who will monitor and when monitoring will occur.
| We don't always have enough time to be present to monitor. We don't know how to give difficult feedback. | 4.3. We are continuously designing a culture of accountability at all levels | 4.3.1. Admins will examine the scheduling needed to assure that employees are regularly observed and offered adequate support for mastering their assigned duties.
4.3.2. Trainers will design formal instructional modules for providing positive and supportive feedback. This includes guidance on ways to ask those monitored for their 360' feedback.
4.3.3. Trainers will design modules on how to respond effectively when offered feedback.
4.3.4. Three months after initial implementation and quarterly after that, trainers will solicit feedback from staff regarding the effectiveness of the training and monitoring systems.
4.3.5. Admins will develop a system of appetitive consequences for individuals observed to be engaging in specified monitoring tasks (see details in Section 5.0 of this document).
4.3.6. Admins will develop a system of graduated sanctions for individuals not engaging in specified monitoring tasks (see details in section 5.0 of this document).
5.0 Graduated Rfcers & Sanctions | We are not currently 'comfortable being uncomfortable' when asking why a person has done something. We are unclear who can and should not have those converstations | 5.1. We hold each other accountable to programs and protocols. We are willing to offer support to each other in service of ACME's stated values | 5.1.1. Associates will offer support when a colleague may be straying from company values (e.g., offer to assist when someone is gruff with a client. "I wonder if I can lend you a hand?")
5.1.2. Associates will state when employee is going towards their value (e.g., "I like that you are actively engagged with your child. I like how enthusiastic you are with your child!")
| We do not understand what actions would result in corrective plan and how many received could result in possible termination | 5.2. We have a performance level system for reinforcing desired behavior and sanctioning misconduct (Level 1,2,3) | 5.2.1. Associates will select from a list of desirable consquences after complying with Handbook, company values and BACB Ethics across levels for x months, as observed in regular bi-weekly supervision meetings.
5.2.2. When associates are observed engaging in a pattern of behavior that does not conform to the Handbook, company values, and BACB Compliance Code, they will receive corrective plan (each level is severity (e.g - 2 at level 1 could result in termination, 3 at level 2, 4 at level 3).
5.2.3. Except in instances of eggregious behavior warranting suspension or dismissal, associates observed engaging in a single instance of behavior that does not conform to the Handbook, company values, and BACB Compliance Code, will receive notice and, be offered an opportunity to be monitored for more effective performance over the following month.
| Not knowing everything in the handbook | 5.3. We provide detailed orientation of the handbook | 5.3.1 Associates will spend set # of hours going over the handbook at orientation.
5.3.2. Associates will review changes made to the handbook when informed.
5.3.3. Associates will review at least one section of the Handbook at all inservices.
6.0 Conflict Resolution | We are uncomfortable giving and receiving feedback because in the past when we did so, it resulted in hard feelings and conflicts. | 6.1. We provide and receive constructive feedback to each other regularly. | 6.1.1 By March 15, 2020, trainers will develop a process map to teach employees how to give and receive feedback. Colleagues will be encourages to ask each other questions such as, "Hey, I noticed that you spent a half hour chatting with Mrs. X. We missed you on the floor during that time. Was there a situation you were addressing that we should all know about?"
6.1.2. Employees will ask trainers or supervisors for coaching and support if colleagues asked about their conduct are dissmissive or rebuff the questions.
6.1.3. Associates will end feedback training when they have reached fluency and are able to enagage in a correct response within 1s across 10 scenarios.
6.1.4. Trainers will review Stokes & Baer, 1977 (An implicit technology of generalization) to develop procedures for supporting a generalized repertoire for offering and receiving constructive feedback.
6.1.5. Using BST, trainers will teach four skills to associates for use when addressing difficult topics with their colleagues. The four skills ("SSTS") are 1) Strike up a friendly conversation first; 2) Stand side-by-side instead of facing the person; 3) Take a "did you know?" approach, and 4) Suggest an alternate behavior.
| We reinforce each other complaining and gossiping. We punish or extinguish efforts to directly provide feedback to colleagues. | 6.2. We kindly redirect complaining, rumor, and gossip. We reinforce each other for offering supportive feedback. | 6.2.1. Associates will use "Stop, Redirect, Praise" to respond to rumor, gossip, and unproductive complaining. That is, they will 1) ask colleagues to kindly stop the behavior, 2) give an alternative (e.g., "Would you like help figuring out how to talk directly to X about this?", and 3) reinforce successive approximations toward a more skillful response.
6.2.2. Associates will ask for support from colleagues if they have been rebuffed, dismissed, or if asking about questionable conduct has resulted in an ongoing conflict.
| We do not reinforce sensible, creative solutions to ethical problems. We do not have a way of reviewing decisions that have ethical ramifications and their results. | 6.3. We have an Ethics Committee that reviews ethical questions, offers clarification, reviews specific instances of unethical conduct, and makes recommendations to admin regarding best practices. | 6.3.1. By March 15, 2020, ACME admins will form an Ethics Committee. This committee will be tasked with reviewing questions pertaining to ethical practice in situations where BACB Conduct Code items seem to conflict with each other.
6.3.2. Ethics Committee membership will rotate every six months. The committee will develop strategies to help maintain its focus on challenging issues that threaten to weaken ACME if not addressed.
6.3.3. Associates will post appropriate ethical questions on an easily accessible shared Google document/form.
6.3.4. Associates serving on the Ethics Committee will review ethical concerns that are added to the relevant google document.
7.0 Authority for Groups to Self-Govern | Our offices (Colony, River, Paw Paw) and our service groups (Techs, Trainers, Supervisors, Admins, Billing) want a stronger sense of unity, to be heard, to engage in meaningful communication, and to establish trust. Trust = fulfillment. | 7.1. We have seven multi-level disscussion boards for our offices (Colony, River, Paw Paw) and service groups (Techs, Trainers, Supervisors, Admins, Billing). | 7.1.1. By April 1, 2020, admins will develop a discussion board for each office and sevice group using Trello, Slack, or Google Docs.
7.1.2. Admins will distribute satisfaction surveys once every 3 months to feel the pulse of the organization's morale.
| Our offices don't have a forum in which to openly discuss tech and trainer concerns | 7.2. We have regularly scheduled center-based meetings and get-togethers | 7.2.1. Admins will schedule quarterly meetings and get-togethers to bond, celebrate, and discuss issues.
7.2.2. Associates will discuss client-based & center-based policies & procedures.
8.0 Inter-Group Relations | We need more robust systems for ongoing communication between centers and between groups within centers | 8.1. We have a platform for communication between admins and clinical supervisors at the three offices | 8.1.1 Beginning April 1, 2020, admins and clinical directors will meet quarterly via Zoom or by posting on an online bulletin board to ask questions and share resources.
8.1.2. Admins will suggest topics initially to guide the formation of these collaborative groups.
| Company wide trainings / in services | 8.2. ACME hosts inclusive staff development / training days with all centers present to help establish cohesive company culture | 8.2.1. ACME will host an annual training at a centralized location
8.2.2. Admins will explore feasibility of renting a venue
8.2.3. Associates will attend either in person, via Zoom, or video recording
8.2.4. Assure CE's for individuals and disseminate information to all associates
| Centralized social event (company wide picnic) | 8.3. ACME promotes unity and cohesiveness with individuals from all centers in a family-oriented manner | 8.3.1. ACME will host an annual get-together for associates from all centers.
8.3.2. Admins will establish a date for a company wide social event (June?)
| To strengthen our market position, we need community outreach | 8.4. We are actively building and strenthening our relationships with schools, residential and community providers, and other ABA service organizations | 8.4.1. Admins will evaluate whether this is to be initiated by an internal employee or would it be more profitable to hire an outside individual (part-time or volunteer).
8.4.2. Admins will, based on the cost analysis, determine a feasible outreach plan with a timeline for implementation by April 1, 2020.

## Implementation Plan
Activity | Item # | NOTES | Duration (Days) | Start Date | Finish Date | Responsible Parties: | Accountable to: | % Complete | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-22 | 2020-03-29 | 2020-04-05 | 2020-04-12 | 2020-04-19 | 2020-04-26 | 2020-05-03 | 2020-05-10 | 2020-05-17 | May 24 | 2020-05-31 | 2020-06-07 | Nub 14 | 2020-06-21 | 2020-06-28 | 2020-07-05 | 2020-07-12 | 2020-07-19 | 2020-07-26 | 2020-08-02 | 2020-08-09 | 2020-08-16 | 2020-08-23 | 2020-08-30 | 2020-09-06 | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-11 | 2020-10-18 | 2020-10-25 | 2020-11-01 | 2020-11-08 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20 | 2020-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21
STRONG GROUP IDENTITY & SENSE OF PURPOSE | 1
1.1. Families report that they felt supported & validated | 1.1.
1.1.1 Directors will use BST to teach supervisors active listening skills once per quarter, beginning March, 2020 | 1.1.1 |  | 1 day | 2020-07-08 | 2020-07-22 | Four Directors | Jenna
1.1.1.1 Program supervisors will meet with directors for a one-half hour training | 1.1.1.1 |  | 1 day | 2020-07-08 | 2020-07-22 | Four Directors | Jenna
1.1.1.2 Training to be developed by lead person | 1.1.1.2 |  | 7 days | 2020-03-09 | 2020-04-01 | Fran | Jenna
1.1.1.3 Give training to trainers | 1.1.1.3 |  | 1 day | 2020-07-08 | 2020-07-22 | Fran | Jenna
1.1.1.4 Trainers to teach associates | 1.1.1.4 |  | 1 day | 2020-07-20 | 2020-07-22 | Trainers | Fran
1.1.2 Associates will restate what others have said to them (e.g., "So, what I hear you saying is…") during conversations with each other, kids, and teachers, with a goal of 5x per week when speaking to staff and giving goals for next time, during group activities, and during interaction with clients | 1.1.2 |  | 6 weeks | 2020-07-21 | 2020-07-31 | Trainers | Fran
1.1.2.1 Trainers will record individual employees' use of active listening with a goal of 5x per week when speaking to staff and giving goals for next time, during group activities, and during interaction with clients | 1.1.2.1 |  | 2 weeks | 2020-07-21 | 2020-07-31 | Trainers | Fran
1.1.2.2 Trainers will record data on supervison feedback form | 1.1.2.2 |  | 2 weeks | 2020-07-21 | 2020-07-31 | Trainers | Fran
1.1.2.3 Collect baseline data | 1.1.2.3 |  | 2 weeks | 2020-03-10 | 2020-03-16 | Trainers | Fran
1.1.3. Associates will express empathy (e.g., "That sounds hard. Anyone would feel that way.") during conversations with each other, kids, and teachers, as observed by colleagues after initial training and documented on the biweekly employee satisfaction survey. | 1.1.3 |  | 6 weeks | 2020-07-21 | 2020-07-31 | Trainers | Fran
1.1.3.1 Collect baseline data by 7/21/2020 and follow up data on-going. | 1.1.3.1 |  | 4 weeks | 2020-07-10 | 2020-07-24 | Directors | Fran
1.2. Staff report that the way supervisors talk to them is relatable | 1.2.
1.2.1. Admins will use BST to teach supervisors and staff relatable ways to discuss company initiatives during virtual meetings/or purchased training in August. | 1.2.1 |  | 4 weeks | 2020-07-13 | 2020-08-30 | All | Jenna/Fran
1.2.1.1 Assign a person to research if training will be developed in house or outsourced |  |  | 2 weeks | 2020-07-01 | 2020-07-12 | Fran | Jenna/Fran
1.2.2. Associates will use non-aversive ways to express ACT concepts (e.g.,. Yeah, I'm working on taking my thoughts lightly, too") (feedback surveys) | 1.2.2 |  | 4 weeks | 2020-07-31 | 2020-08-09 | Center Clinical Directors | Jenna/Fran
1.3 Other important Items needed for a strong foundation that may have come about recently
EQUIVALENT RESOURCES / REINFORCERS | 2
2.1. Every center gets fair distribution of ACME resources | 2.1.
2.1.1. Admins will provide quarterly reports about available resources, where the company is at, to see if the resources are available, beginning March, 2020 - On hold due to time and Corona variables | 2.1.1 | Due to Corona - PPE, staff, Distance challenges to supplies, Admins don't have enough time
2.1.1.1 Resource of current PPE supplies available for everyone | 2.1.1.1 | PPE inventory - Google Sheet, Count cloth masks, hand sanitizer by ounces, gloves/size and masks by boxes (whole/half/quarter), wipes container, count what is currently with center clients, updated weekly on Friday |  |  | 2020-05-29 | 6/3/2020, first update and then ongoing | Kris- Techs up and at center, Jenna, Raquel/Leandra
2.1.2. Admins will analyze resources and redistribute yearly, beginning _____ On hold due to time and Corona variables | 2.1.2
2.2. We have written clearly defined job roles | 2.2.
2.2.1. Admins will clearly define all of the roles for each position for the company, beginning _____ | 2.2.1 | Give access to current job roles, clarify responsibilites based on time in role, more transparency for other responsibilites, tech level behaviors in drive in Values folder - understanding some of it is subjective and letting people know expectations, need to continue working on job descriptions for roles beyond techs |  |  |  | 30 minutes on your own job description/roles by 6/12/2020 - supervisors with 15 or less billable hours will complete by a set date (determined at next meeting) | Rachel/Erica work on tech levels, Rachel to help with lead tech
2.2.2. Admins will ask associates for input in writing job descriptions, beginning March, 2020 | 2.2.2 | Ask at least one tech from Columbo to join this meeting (preferably not a lead tech or grad student), Kait will represent Durango |  |  |  |  | Assign as a task for those not on schedule and will be visible for all in classroom
2.2.3. Associates will group responsibilities for each role | 2.2.3 | Create one for techs, review the current job responsibilites at specific meetings next week
2.3. We hold regular supervisory meetings and reschedule cancelled meetings as needed or requested by staff | 2.3.
2.3.1. Supervisors will provide regular bi-weekly meetings or reschedule if unable to meet as scheduled, beginning March, 2020 | 2.3.1 | Currently met and will reevaluate in the future
2.3.2. Supervisors will distribute supervision time among staff/clients equitably and provide rationales as needed when there are notable imbalances | 2.3.2 | Currently met and will reevaluate in the future
3.1. We have codified systems for decision-making, on-boarding staff, piloting, and implementing new strategies | 3.1.
3.1.1. ACME will make organizational decisions in teams that include representatives from each site and position (tech, lead, trainer, BCBA, admin). | 3.1.1
3.1.2. Decision teams will provide rationales for decisions and provide associates time to comment prior to implementation. When possible, rationales will refer back to organizational values. | 1.1.2
3.2. Decision teams collect data, evaluate, revise, and report back the community on the effectiveness of inititives | 3.2.
3.2.1. Associates will keep track of decisions and utilize rotating committee for reviewing these decisions. | 3.2.1
3.2.2. Associates will make data based decisions and have frequent revisions during this process. | 3.2.2
3.3. Our decision teams include people from all walks of life. When this is impracticable, we strive toward cultural competence and awareness of our biases, privilege, and power. | 3.3.
3.3.1. Associates will review decisions for their cultural competance, discussing them in light of culture, privledge, and bias. | 3.3.1
3.3.2. Associates will develop a system for how to handle clients behaviors that are offensive, and also be aware of our own bias. | 3.3.2
3.3.3. ACME will write diversity goals for recruiting members of decision teams. | 3.3.3
MONITORING AGREED UPON BEHAVIORS | 4
4.1. We provide clear performance expectations to employees at all levels of the organization. | 4.1
4.1.1. By April 1, 2020, trainers (with support from supervisors, lead techs, and admins) will design modules that specify the parties responsible for monitoring and the scheduled frequency of monitoring. For example, monitors will shadow at least a half hour per shift during a tech's first month, a half hour per week on the average after that until a new hire has completed their probationary period, and a half hour per month after that. | 4.1.1
4.1.2. Trainers, supervisors, lead techs, and admins will clearly specify the boundaries of the monitoring tasks. | 4.1.2
4.1.3. Trainers will create job aids that correspond to the job description for every role. | 4.1.3
4.1.4. Trainers and others involved in designing systems for monitoring agreed upon behaviors will establish an ongoing collaboration with admin. | 4.1.4
4.2. Our monitoring schedules assure that everyone is supported enough to master their jobs. | 4.2
4.2.1. Trainers, supervisors, lead techs, and admins will provide a written, detailed and consistent monitoring schedule. The schedule will specify who will monitor and when monitoring will occur. | 4.2.1
4.3. We are continuously designing a culture of accountability at all levels | 4.3
4.3.1. Admins will examine the scheduling needed to assure that employees are regularly observed and offered adequate support for mastering their assigned duties. | 4.3.1
4.3.2. Trainers will design formal instructional modules for providing positive and supportive feedback. This includes guidance on ways to ask those monitored for their 360' feedback. | 4.3.2
4.3.3. Trainers will design modules on how to respond effectively when offered feedback. | 4.3.3
4.3.4. Three months after initial implementation and quarterly after that, trainers will solicit feedback from staff regarding the effectiveness of the training and monitoring systems. | 4.3.4
4.3.5. Admins will develop a system of appetitive consequences for individuals observed to be engaging in specified monitoring tasks (see details in Section 5.0 of this document). | 4.3.5
4.3.6. Admins will develop a system of graduated sanctions for individuals not engaging in specified monitoring tasks (see details in section 5.0 of this document). | 4.3.6
GRADUATED REINFORCERS & SANCTIONS | 5
5.1. We hold each other accountable to programs and protocols. We are willing to offer support to each other in service of ACME's stated values | 5.1.
5.1.1. Associates will offer support when a colleague may be straying from company values (e.g., offer to assist when someone is gruff with a client. "I wonder if I can lend you a hand?") | 5.1.1
5.1.2. Associates will state when employee is going towards their value (e.g., "I like that you are actively engagged with your child. I like how enthusiastic you are with your child!") | 5.1.2
5.2. We have a performance level system for reinforcing desired behavior and sanctioning misconduct (Level 1,2,3) | 5.2.
5.2.1. Associates will select from a list of desirable consquences after complying with Handbook, company values and BACB Ethics across levels for x months, as observed in regular bi-weekly supervision meetings. | 5.2.1
5.2.2. When associates are observed engaging in a pattern of behavior that does not conform to the Handbook, company values, and BACB Compliance Code, they will receive corrective plan (each level is severity (e.g - 2 at level 1 could result in termination, 3 at level 2, 4 at level 3). | 5.2.2
5.2.3. Except in instances of eggregious behavior warranting suspension or dismissal, associates observed engaging in a single instance of behavior that does not conform to the Handbook, company values, and BACB Compliance Code, will receive notice and, be offered an opportunity to be monitored for more effective performance over the following month. | 5.2.3
5.3. We provide detailed orientation of the handbook | 5.3.
5.3.1. Associates will spend set # of hours going over the handbook at orientation. | 5.3.1
5.3.2. Associates will review changes made to the handbook when informed. | 5.3.2
5.3.3. Associates will review at least one section of the Handbook at all inservices. | 5.3.3
FAIR & FAST CONFLICT RESOLUTION | 6
6.1. We provide and receive constructive feedback to each other regularly. | 6.1.
6.1.1 By March 15, 2020, trainers will develop a process map to teach employees how to give and receive feedback. Colleagues will be encourages to ask each other questions such as, "Hey, I noticed that you spent a half hour chatting with Mrs. X. We missed you on the floor during that time. Was there a situation you were addressing that we should all know about?" | 6.1.1
6.1.2. Employees will ask trainers or supervisors for coaching and support if colleagues asked about their conduct are dissmissive or rebuff the questions. | 6.1.2
6.1.3. Associates will end feedback training when they have reached fluency and are able to enagage in a correct response within 1s across 10 scenarios. | 6.1.3
6.1.4. Trainers will review Stokes & Baer, 1977 (An implicit technology of generalization) to develop procedures for supporting a generalized repertoire for offering and receiving constructive feedback. | 6.1.4
6.1.5. Using BST, trainers will teach four skills to associates for use when addressing difficult topics with their colleagues. The four skills ("SSTS") are 1) Strike up a friendly conversation first; 2) Stand side-by-side instead of facing the person; 3) Take a "did you know?" approach, and 4) Suggest an alternate behavior. | 6.1.5
6.2. We kindly redirect complaining, rumor, and gossip. We reinforce each other for offering supportive feedback. | 6.2.
6.2.1. Associates will use "Stop, Redirect, Praise" to respond to rumor, gossip, and unproductive complaining. That is, they will 1) ask colleagues to kindly stop the behavior, 2) give an alternative (e.g., "Would you like help figuring out how to talk directly to X about this?", and 3) reinforce successive approximations toward a more skillful response. | 6.2.1
6.2.2. Associates will ask for support from colleagues if they have been rebuffed, dismissed, or if asking about questionable conduct has resulted in an ongoing conflict. | 6.2.2
6.3. We have an Ethics Committee that reviews ethical questions, offers clarification, reviews specific instances of unethical conduct, and makes recommendations to admin regarding best practices. | 6.3.
6.3.1. By March 15, 2020, ACME admins will form an Ethics Committee. This committee will be tasked with reviewing questions pertaining to ethical practice in situations where BACB Conduct Code items seem to conflict with each other. | 6.3.1
6.3.2. Ethics Committee membership will rotate every six months. The committee will develop strategies to help maintain its focus on challenging issues that threaten to weaken ACME if not addressed. | 6.3.2
6.3.3. Associates will post appropriate ethical questions on an easily accessible shared Google document/form. | 6.3.3
6.3.4. Associates serving on the Ethics Committee will review ethical concerns that are added to the relevant google document. | 6.3.4
AUTHORITY FOR GROUPS TO SELF-GOVERN | 7
7.1. We have seven multi-level disscussion boards for our offices (Colony, River, Paw Paw) and service groups (Techs, Trainers, Supervisors, Admins, Billing). | 7.1.
7.1.1. By April 1, 2020, admins will develop a discussion board for each office and sevice group using Trello, Slack, or Google Docs. | 7.1.1
7.1.2. Admins will distribute satisfaction surveys once every 3 months to feel the pulse of the organization's morale. | 7.1.2
7.2. We have regularly scheduled center-based meetings and get-togethers | 7.2.
7.2.1. Admins will schedule quarterly meetings and get-togethers to bond, celebrate, and discuss issues. | 7.2.1
7.2.2. Associates will discuss client-based & center-based policies & procedures. | 7.2.2
INTER-GROUP RELATIONS (POLYCENTRIC GOVERNANCE) | 8
8.1. We have a platform for communication between admins and clinical supervisors at the three offices | 8.1.
8.1.1 Beginning April 1, 2020, admins and clinical directors will meet quarterly via Zoom or by posting on an online bulletin board to ask questions and share resources. | 8.1.1
8.2. ACME hosts inclusive staff development / training days with all centers present to help establish cohesive company culture | 8.2.
8.2.1. ACME will host an annual training at a centralized location | 8.2.1
8.2.2. Admins will explore feasibility of renting a venue | 8.2.2
8.2.3. Associates will attend either in person, via Zoom, or video recording | 8.2.3
8.2.4. Assure CE's for individuals and disseminate information to all associates | 8.2.4
8.3. ACME promotes unity and cohesiveness with individuals from all centers in a family-oriented manner | 8.3.
8.3.1. ACME will host an annual get-together for associates from all centers. | 8.3.1
8.3.2. Admins will establish a date for a company wide social event (June?) | 8.3.2
8.4. We are actively building and strenthening our relationships with schools, residential and community providers, and other ABA service organizations | 8.4.
8.4.1. Admins will evaluate whether this is to be initiated by an internal employee or would it be more profitable to hire an outside individual (part-time or volunteer). | 8.4.1
8.4.2. Admins will, based on the cost analysis, determine a feasible outreach plan with a timeline for implementation by April 1, 2020. | 8.4.2